## Daywise Plan
Activities To Be Performed
Day 1 | Create tables & provide foreign key relationship
Create backend Project first, create API and test using Postman
Functionalities to be completed:
User verification- user login, admin login, forgot username, forgot/reset password
SignUp- newAccountOPEN,RegisterForNetBanking
Admin- PermitnewAccount, RejectNewUser
Day 2 | Create API and test using Postman
Functionalities to be complete
USER- useraccountdetails,useraccountsummary,userstatements, balance enquiry
Day 3 | Create API and test using Postman, Swagger
Functionalities to be complete
Includenewbeneficiary
Fund Transfer
Remove Beneficiary
Day 4 | Create User Interface and connect with backend
NewAccountOpen for USER
Register User for NetBanking
USER Login
Admin Login
Day 5 | Create User Interface and connect with backend
Forgot UserName
Forgot password
Reset Password
User Account Details
User Account Summary
User Statements
Balance Enquiry
Day 6 | Create User Interface and connect with backend
Functionalities to be complete
IncludeNewBeneficiary
Fund Transfer
Remove beneficiary